## Sheet1
Reserve Fund Plan for TUSCAWILLA HILLS CITIZEN'S ASSOCIATION Charles Town, West Virginia | [6 empty] | COMPONENT DATA AND ASSET REPLACEMENT SCHEDULE TABLE 1 2012 Through 2031
Component No. | Component | Quantity | Unit of Measurement | Unit Cost | Total Asset Base | Typical Service or Cycle Life in Yrs | 1st Cycle Year | Percentage of Replacement | Cost For 1st Cycle | 2nd Cycle Year | Percentage of Replacement | Cost For 2nd Cycle | 3rd Cycle Year | Percentage of Replacement | Cost For 3rd Cycle | Photo (#1, #2) Maintenance Protocol (7.1, 7.2) | DISCUSSION
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 ASPHALT COMPONENTS
1.1 | Asphalt Life-Extension Overlay Repairs | 94619 | SY | 11.2 | 1059732.8 | 25 | 2012 | 1% | 10597.328 | 2014 | 7% | 78698.9369 | 2016 | 6% | 71564.3162 |  | The asphalt pavement throughout the community appears to range from poor to improving good condition. The thickness of the pavement could not be visually determined, although it is reported to be originally a 6"aggregate sub-base, with 2" base asphalt and 1" wear course. This is quite minimal for pavement serving heavy trash trucks and moving vans. The recent repair overlays have reportedly been in the 1 1/2" to 2" thickness range, although this could not be confirmed. The overlays are reportedly under warranty for three years. We don't anticipate cracking to show up until four to five years, so this may not be important. Restoration includes edgemilling where there are curbs, full milling where there is severe deflection, and overlay with 1-½" new compacted asphalt at a minimum. Core sampling should be used to determine the depth and condition of the sub-base and pavement prior to restoration. Costs include re-striping, but not replacement of any inadequate sub-base. The cost is an aggregate average for all types of repair, but principally based on overlays like the type recently installed. See the Asphalt Pavement Report, Section 7, for additional details. It should be noted that this is only a rough projection of anticipated replacement requirements and that actual experience may be faster or slower than scheduled. The new schedule is based on information gathered over four years of observation and, therefore, is somewhat more reliable. Future updates will help continue to refine the schedules. This line items replaces both asphalt repair and restoration line items previously scheduled.
2 CONCRETE COMPONENTS
2.1 | Concrete Sidewalks | 48409 | SF | 8.5 | 411476.5 | 5 | 2013 | 1% | 4238.2079 | 2018 | 2% | 9826.4892 | 2023 | 2% | 11391.5942 |  | Concrete sidewalks throughout the community are generally 4' or 5' wide. The thickness of the concrete could not be visually determined although the thickened edge at pavements appears to be generally 8". Most sidewalks appear to be in good condition. We observed approximately seven trip hazards that should be repaired as soon as practicable, and the scaled edges at the Central Mail Station may be a hazard. Over time, additional cracking, settlement and scaling should be anticipated. Replacement of additional scaled sections should be addressed with each replacement cycle as they will tend to deteriorate more quickly over time. Cyclic repairs are scheduled as full replacement at one time is not appropriate or anticipated. Concrete repairs are scheduled to coincide with other concrete components to promote cost efficiencies.
2.2 | Concrete Curbs & Gutters | 6316 | LF | 32 | 202112 | 5 | 2013 | 1% | 2081.7536 | 2018 | 1% | 2413.323 | 2023 | 1% | 2797.7028 |  | The drivelanes and parking bays of the townhome sections are lined with standard-profile, cast-in-place, concrete curbs. Most curbs are generally in continuing good condition with a small number of deficient sections observed. As curbs age, cracks, vehicle impact damage, and settlement should be anticipated. Cyclic repairs are scheduled as full replacement at one time is not appropriate or anticipated. Concrete are scheduled to coincide with other concrete components to promote cost efficiencies.
3 SITE FEATURES
3.1 | Entrance Features | 1 | LS | 6500 | 6500 | 25 | 2030 | 100% | 11065.8149 | 2055 | 100% | 23169.359 |  |  |  |  | The entrance features on each side of Tuscawilla Drive at Route 51 consist of a painted polyvinyl chloride (PVC) panel sign approximately 10' by 3' supported on each side by 7' sections of PVC picket fencing. The structures appear to be in continuing good condition with no damage or deterioration observed. Other than cleaning and replacement of damaged components, this type of material requires little maintenance throughout its long useful service life.
3.2 | Central Mail Station Re-Roofing | 205 | SF | 5.75 | 1178.75 | 20 | 2028 | 100% | 1891.5477 | 2048 | 100% | 3416.3456 |  |  |  |  | The 3/12 pitched roof has an asphalt shingle covering, which has recently been replaced and is in good condition. Pre-finished replacement aluminum gutters and downspouts are installed at roof terminations and are in good condition. Re-roofing projects include replacement of shingles, deteriorated sheathing, and gutters and downspouts.
3.3 | Central Mailboxes Inventory | 1 | LS | 30000 | 30000 | 40 | 2048 | 100% | 86948.3498 | [7 empty] | This building has been enlarged and reconfigured since the previous evaluation. Mailboxes are of two different configurations: Built-in and free standing including parcel box modules. Most of the in-wall modules are replacements that were, reportedly, provided by the postal service at no charge. They appear to be in good condition. The older modules appear to be in continuing good, serviceable condition. Of the three free-standing modules, two have new bases, and all appear to be in good, serviceable condition. We understand that additional in-wall modules are stored for future use.
3.4 | Summit Point Mail Station Re-Roofing | 436 | SF | 5.75 | 2507 | 20 | 2023 | 100% | 3470.2743 | 2043 | 100% | 6267.7014 |  |  |  |  | The 3/12 pitched roof has an asphalt shingle covering. It appears to be in continuing good condition with no deteriorated shingles or deflection of the roof sheathing observed. Pre-finished aluminum gutters and downspouts are installed at all roof terminations. Downspouts appear to be properly directed away from building foundations. All components appear to be in good condition. Re-roofing projects include replacement of shingles, deteriorated sheathing, and gutters and downspouts.
3.5 | Summit Point Mailboxes Inventory | 1 | LS | 30000 | 30000 | 40 | 2048 | 100% | 86948.3498 | [7 empty] | This building has been reconfigured since the previous evaluation. Mailboxes at this station are replacement, in-wall modules that were, reportedly, provided by the postal service at no charge with additional replacement modules stored within the building. They appear to be in good condition.
3.6 | Tot Lot & Outdoor Furniture | 1 | LS | 29200 | 29200 | 15 | 2012 | 55% | 16060 | 2027 | 100% | 45492.6486 | 2042 | 100% | 70876.0642 |  | One tot lot is located within the community. Equipment consists of new wood borders in good condition, a metal swing set and climbing dome in continuing good condition, wood benches and two spring toys in continuing good condition, and a small wood post play module that has deteriorated significantly since the previous evaluation. We observed weakened and one missing ladder rung and warped and split wood components. We have budgeted a near-term percentage for replacement of the play module with costs are based on replacement with U.S. Consumer Product Safety Commission (CPSC)-compliant play modules. Preventive maintenance will improve appearance and extend the useful service lives of tot lot components. Frequent, periodic safety checks of all components should be conducted to prevent personal injury.
3.7 | Basketball Court Restoration | 296 | SY | 12.5 | 3700 | 20 | 2018 | 100% | 4417.9935 | 2038 | 100% | 7979.3877 |  |  |  |  | A basketball court is located within the community at the recreation area. The court appears to be in continuing fair, but serviceable condition, with one large crack across the center as well as a repair patch. Filling the crack with a rubberized asphaltic material would prevent water from infiltrating beneath the court and may extend the useful service life by preventing freeze/thaw damage. Color coating would seal the surface and possibly extend the service life.
3.8 | Basketball Standards | 2 | EA | 2200 | 4400 | 40 | 2018 | 100% | 5253.8301 | 2058 | 100% | 17138.1924 |  |  |  |  | Painted metal post standards with backboards are constructed at each end of the court. They appear to be in continuing serviceable condition, but would benefit from rust removal and repainting. They are scheduled for replacement coinciding with the court restoration project.
3.9 | Split-Rail Fencing | 1916 | LF | 13 | 24908 | 20 | 2014 | 10% | 2642.4897 | 2017 | 10% | 2887.5199 | 2020 | 10% | 3155.2709 |  | Wood split-rail fencing is constructed adjacent to the perimeter at Summit Point Road. We understand that components from the main entrance fencing, that was replaced with vinyl fencing, was used to replace deteriorated timbers and posts. The fencing generally appear to be in good condition. This category includes smaller sections of fencing located throughout the community, most of which appear to be somewhat deteriorated. We have budgeted a periodic allowance to address repairs/replacements as necessary.
3.10 | Vinyl Fencing | 264 | LF | 10.25 | 2706 | 30 | 2041 | 100% | 6376.8663 | [7 empty] | Vinyl three-rail fencing has been installed replacing the split rail fencing adjacent to the entrance signs and at another perimeter location at Fenway Drive. All components appear to be in good condition and should provide a long service life with little or no maintenance other than replacing or repairing damaged components.
3.11 | Storm Water Drainage System Allowance | 1 | LS | 7500 | 7500 | 7 | 2013 | 100% | 7725 | 2020 | 100% | 9500.7756 | 2027 | 100% | 11684.7556 |  | Storm water drainage is provided by concrete yard drains, curb drop inlets, underground structures, and approximately four storm water management areas created by earthen impoundment structures. All observable components appear to be in continuing good condition. Vegetation should be periodically controlled as woody vegetation diminishes capacity over time. Though storm water drainage systems are a long life component and catastrophic failure is not anticipated, it is prudent to plan for localized repairs and repairs to ancillary damage as the system ages. This category may also be used to address localized erosion issues.
1815921.05

## Sheet2
Reserve Fund Plan for TUSCAWILLA HILLS CITIZEN'S ASSOCIATION Charles Town, West Virginia |  |  | CALENDAR OF EXPENDITURES TABLE 2 2012 Through 2031
YEAR | COMPONENT NO. | COMPONENT | PRESENT COST 2012 | FUTURE COST (INFLATED) | TOTAL ANNUAL EXPENDITURES | ACTION
1 | 2 | 3 | 4 | 5 | 6 | 7
2012 |  |  |  |  | 2012
| 1.1 | Asphalt Life-Extension Overlay Repairs | 10597.328 | 10597.328 | TOTAL EXPENDITURES
| 3.6 | Tot Lot & Outdoor Furniture | 16060 | 16060
26657.328
2013 |  |  |  |  | 2013
| 2.1 | Concrete Sidewalks | 4114.765 | 4238.2079 | TOTAL EXPENDITURES
| 2.2 | Concrete Curbs & Gutters | 2021.12 | 2081.7536
| 3.11 | Storm Water Drainage System Allowance | 7500 | 7725
14044.9615
2014 |  |  |  |  | 2014
| 1.1 | Asphalt Life-Extension Overlay Repairs | 74181.296 | 78698.9369 | TOTAL EXPENDITURES
| 3.9 | Split-Rail Fencing | 2490.8 | 2642.4897
81341.4266
2015 |  |  |  |  | 2015
NO EXPENDITURES
2016 |  |  |  |  | 2016
| 1.1 | Asphalt Life-Extension Overlay Repairs | 63583.968 | 71564.3162 | TOTAL EXPENDITURES
71564.3162
2017 |  |  |  |  | 2017
| 3.9 | Split-Rail Fencing | 2490.8 | 2887.5199 | TOTAL EXPENDITURES
2887.5199
2018 |  |  |  |  | 2018
| 1.1 | Asphalt Life-Extension Overlay Repairs | 63583.968 | 75922.583 | TOTAL EXPENDITURES
| 2.1 | Concrete Sidewalks | 8229.53 | 9826.4892
| 2.2 | Concrete Curbs & Gutters | 2021.12 | 2413.323
| 3.7 | Basketball Court Restoration | 3700 | 4417.9935
| 3.8 | Basketball Standards | 4400 | 5253.8301
97834.2188
2019 |  |  |  |  | 2019
NO EXPENDITURES
2020 |  |  |  |  | 2020
| 1.1 | Asphalt Life-Extension Overlay Repairs | 190751.904 | 241638.805 | TOTAL EXPENDITURES
| 3.9 | Split-Rail Fencing | 2490.8 | 3155.2709
| 3.11 | Storm Water Drainage System Allowance | 7500 | 9500.7756
254294.8515
2021 |  |  |  |  | 2021
NO EXPENDITURES
2022 |  |  |  |  | 2022
| 1.1 | Asphalt Life-Extension Overlay Repairs | 190751.904 | 256354.6082 | TOTAL EXPENDITURES
256354.6082
2023 |  |  |  |  | 2023
| 2.1 | Concrete Sidewalks | 8229.53 | 11391.5942 | TOTAL EXPENDITURES
| 2.2 | Concrete Curbs & Gutters | 2021.12 | 2797.7028
| 3.4 | Summit Point Mail Station Re-Roofing | 2507 | 3470.2743
| 3.9 | Split-Rail Fencing | 2490.8 | 3447.8497
21107.421
2024 |  |  |  |  | 2024
| 1.1 | Asphalt Life-Extension Overlay Repairs | 190751.904 | 271966.6038 | TOTAL EXPENDITURES
271966.6038
2025 |  |  |  |  | 2025
NO EXPENDITURES
2026 |  |  |  |  | 2026
| 1.1 | Asphalt Life-Extension Overlay Repairs | 190751.904 | 288529.37 | TOTAL EXPENDITURES
| 3.9 | Split-Rail Fencing | 2490.8 | 3767.5585
292296.9285
2027 |  |  |  |  | 2027
| 3.6 | Tot Lot & Outdoor Furniture | 29200 | 45492.6486 | TOTAL EXPENDITURES
| 3.11 | Storm Water Drainage System Allowance | 7500 | 11684.7556
57177.4042
2028 |  |  |  |  | 2028
| 1.1 | Asphalt Life-Extension Overlay Repairs | 84778.624 | 136044.8038 | TOTAL EXPENDITURES
| 2.1 | Concrete Sidewalks | 12344.295 | 19808.9697
| 2.2 | Concrete Curbs & Gutters | 4042.24 | 6486.6086
| 3.2 | Central Mail Station Re-Roofing | 1178.75 | 1891.5477
164231.9298
2029 |  |  |  |  | 2029
| 3.9 | Split-Rail Fencing | 2490.8 | 4116.9129 | TOTAL EXPENDITURES
4116.9129
2030 |  |  |  |  | 2030
| 1.1 | Asphalt Life-Extension Overlay Repairs | 42389.312 | 72164.9662 | TOTAL EXPENDITURES
| 3.1 | Entrance Features | 6500 | 11065.8149
83230.7811
2031 |  |  |  |  | 2031
NO EXPENDITURES

## Sheet3
Reserve Fund Plan for TUSCAWILLA HILLS CITIZEN'S ASSOCIATION Charles Town, West Virginia |  |  | CURRENT FUNDING ANALYSIS CASH FLOW METHOD TABLE 3
|  | Beginning Reserve Fund Balance: | Annual Contribution To Reserves: |  |  |  | Contribution Percentage Increase: | Annual Inflation Factor: | Annual Interest Income Factor:
|  | 86906 | 86000 |  |  |  | 3% | 3% | 2%
YEAR | TOTAL ASSET BASE | BEGINNING RESERVE FUND BALANCE | ANNUAL CONTRIBUTION | Bal | Cont | Exp | INTEREST INCOME | CAPITAL EXPENDITURES | ENDING RESERVE FUND BALANCE
1 | 2 | 3 | 4 | 5 | 6 | 7 | 5 | 6 | 7
2012 | 1815921.05 | 86906 | 86000 | 2691.5256 | 937.384 | -289.6658 | 3339.2438 | 26657 | 149588.2438
2013 | 1870398.6815 | 149588.2438 | 88580 | 3019.3423 | 965.5055 | -152.6187 | 3832.2291 | 14045 | 227955.4729
2014 | 1926510.6419 | 227955.4729 | 91237.4 | 4601.1343 | 994.4707 | -883.8844 | 4711.7206 | 81341 | 242563.5934
2015 | 1984305.9612 | 242563.5934 | 93974.522 | 4895.9898 | 1024.3048 | 0 | 5920.2946 | 0 | 342458.4101
2016 | 2043835.14 | 342458.4101 | 96793.7577 | 6912.3024 | 1055.0339 | -777.6436 | 7189.6927 | 71564 | 374877.8604
2017 | 2105150.1942 | 374877.8604 | 99697.5704 | 7566.6681 | 1086.6849 | -31.3822 | 8621.9708 | 2888 | 480309.4017
2018 | 2168304.7001 | 480309.4017 | 102688.4975 | 9694.7358 | 1119.2855 | -1063.1041 | 9750.9172 | 97834 | 494914.8163
2019 | 2233353.8411 | 494914.8163 | 105769.1524 | 9989.5367 | 1152.8641 | 0 | 11142.4007 | 0 | 611826.3695
2020 | 2300354.4563 | 611826.3695 | 108942.227 | 12349.3211 | 1187.45 | -2763.2731 | 10773.498 | 254295 | 477247.0945
2021 | 2369365.09 | 477247.0945 | 112210.4938 | 9632.9251 | 1223.0735 | 0 | 10855.9986 | 0 | 600313.5869
2022 | 2440446.0427 | 600313.5869 | 115576.8086 | 12116.943 | 1259.7657 | -2785.6579 | 10591.0508 | 256355 | 470126.4463
2023 | 2513659.424 | 470126.4463 | 119044.1129 | 9489.1994 | 1297.5587 | -229.3681 | 10557.3899 | 21108 | 578619.9491
2024 | 2589069.2067 | 578619.9491 | 122615.4363 | 11679.0709 | 1336.4854 | -2955.3042 | 10060.252 | 271967 | 439328.6374
2025 | 2666741.2829 | 439328.6374 | 126293.8994 | 8867.5655 | 1376.58 | 0 | 10244.1455 | 0 | 575866.6822
2026 | 2746743.5214 | 575866.6822 | 130082.7163 | 11623.4979 | 1417.8774 | -3176.2183 | 9865.157 | 292297 | 423517.5556
2027 | 2829145.827 | 423517.5556 | 133985.1978 | 8548.429 | 1460.4137 | -621.3194 | 9387.5232 | 57178 | 509712.2766
2028 | 2914020.2018 | 509712.2766 | 138004.7538 | 10288.2139 | 1504.2261 | -1784.6227 | 10007.8173 | 164233 | 493491.8477
2029 | 3001440.8079 | 493491.8477 | 142144.8964 | 9960.815 | 1549.3529 | -44.737 | 11465.4309 | 4117 | 642985.175
2030 | 3091484.0321 | 642985.175 | 146409.2433 | 12978.2415 | 1595.8335 | -904.422 | 13669.653 | 83231 | 719833.0712
2031 | 3184228.5531 | 719833.0712 | 150801.5206 | 14529.3667 | 1643.7085 | 0 | 16173.0752 | 0 | 886807.667
STUDY PERIOD TOTALS |  |  | 2310852.2061 | 181434.8239 | 25187.8586 | -18463.2215 | 188159.4609 | 1699110

## Sheet3.1
Reserve Fund Plan for TUSCAWILLA HILLS CITIZEN'S ASSOCIATION Charles Town, West Virginia |  |  | ALTERNATIVE FUNDING ANALYSIS HYBRID APPROACH CASH FLOW METHOD TABLE 3.1
|  | Beginning Reserve Fund Balance: | Annual Contribution To Reserves: |  |  |  | Contribution Percentage Increase: | Annual Inflation Factor: | Annual Interest Income Factor:
|  | 86906 | 86000 |  |  |  | 3% | 3% | 2%
YEAR | TOTAL ASSET BASE | BEGINNING RESERVE FUND BALANCE | ANNUAL CONTRIBUTION | Bal | Cont | Exp | INTEREST INCOME | CAPITAL EXPENDITURES | ENDING RESERVE FUND BALANCE
1 | 2 | 3 | 4 | 5 | 6 | 7 | 5 | 6 | 7
2012 | 1815921.05 | 86906 | 86000 | 2691.5256 | 937.384 | -289.6658 | 3339.2438 | 26657 | 149588.2438
2013 | 1870398.6815 | 149588.2438 | 69142.4789 | 3019.3423 | 753.6401 | -152.6187 | 3620.3638 | 14045 | 208306.0864
2014 | 1926510.6419 | 208306.0864 | 71216.7532 | 4204.5241 | 776.2493 | -883.8844 | 4096.889 | 81341 | 202278.7286
2015 | 1984305.9612 | 202278.7286 | 73353.2558 | 4082.8658 | 799.5368 | 0 | 4882.4026 | 0 | 280514.3871
2016 | 2043835.14 | 280514.3871 | 75553.8535 | 5662.0022 | 823.5229 | -777.6436 | 5707.8815 | 71564 | 290212.1221
2017 | 2105150.1942 | 290212.1221 | 77820.4691 | 5857.7447 | 848.2286 | -31.3822 | 6674.5911 | 2888 | 371819.1823
2018 | 2168304.7001 | 371819.1823 | 80155.0832 | 7504.9306 | 873.6755 | -1063.1041 | 7315.502 | 97834 | 361455.7675
2019 | 2233353.8411 | 361455.7675 | 82559.7357 | 7295.7518 | 899.8857 | 0 | 8195.6375 | 0 | 452211.1407
2020 | 2300354.4563 | 452211.1407 | 85036.5277 | 9127.5905 | 926.8823 | -2763.2731 | 7291.1997 | 254295 | 290243.8682
2021 | 2369365.09 | 290243.8682 | 87587.6236 | 5858.3855 | 954.6888 | 0 | 6813.0743 | 0 | 384644.566
2022 | 2440446.0427 | 384644.566 | 90215.2523 | 7763.8027 | 983.3294 | -2785.6579 | 5961.4743 | 256355 | 224466.2926
2023 | 2513659.424 | 224466.2926 | 92921.7099 | 4530.7075 | 1012.8293 | -229.3681 | 5314.1687 | 21108 | 301594.1711
2024 | 2589069.2067 | 301594.1711 | 95709.3611 | 6087.484 | 1043.2142 | -2955.3042 | 4175.394 | 271967 | 129511.9263
2025 | 2666741.2829 | 129511.9263 | 98580.642 | 2614.1148 | 1074.5106 | 0 | 3688.6254 | 0 | 231781.1937
2026 | 2746743.5214 | 231781.1937 | 101538.0612 | 4678.3541 | 1106.746 | -3176.2183 | 2608.8817 | 292297 | 43631.1367
2027 | 2829145.827 | 43631.1367 | 104584.2031 | 880.6664 | 1139.9483 | -621.3194 | 1399.2953 | 57178 | 92436.635
2028 | 2914020.2018 | 92436.635 | 107721.7292 | 1865.7739 | 1174.1468 | -1784.6227 | 1255.298 | 164233 | 37180.6622
2029 | 3001440.8079 | 37180.6622 | 110953.381 | 750.4677 | 1209.3712 | -44.737 | 1915.1019 | 4117 | 145932.1451
2030 | 3091484.0321 | 145932.1451 | 114281.9825 | 2945.5463 | 1245.6523 | -904.422 | 3286.7767 | 83231 | 180269.9043
2031 | 3184228.5531 | 180269.9043 | 117710.442 | 3638.6319 | 1283.0219 | 0 | 4921.6538 | 0 | 302902
STUDY PERIOD TOTALS |  |  | 1822642.5449 | 91060.2124 | 19866.4642 | -18463.2215 | 92463.4551 | 1699110
FULLY FUNDED BALANCE GOAL

## Sheet4
Reserve Fund Plan for TUSCAWILLA HILLS CITIZEN'S ASSOCIATION Charles Town, West Virginia | [6 empty] | FUNDING ANALYSIS COMPONENT METHOD TABLE 4
Beginning Reserve Fund Balance:
86906
Component Number | COMPONENT | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
1.1 | Asphalt Life-Extension Overlay Repairs | 43013 | 38536 | 35043 | 35043 | 37177 | 37177 | 118323 | 118323 | 125528 | 125528 | 133173 | 133173 | 141283 | 141283 | 66617 | 66617 | 35337 | 35337 | 37489 | 37489
2.1 | Concrete Sidewalks | 1791 | 1867 | 1867 | 1867 | 1867 | 1867 | 2165 | 2165 | 2165 | 2165 | 2165 | 3764 | 3764 | 3764 | 3764 | 3764 | 4364 | 4364 | 4364 | 4364
2.2 | Concrete Curbs & Gutters | 880 | 459 | 459 | 459 | 459 | 459 | 532 | 532 | 532 | 532 | 532 | 1233 | 1233 | 1233 | 1233 | 1233 | 1429 | 1429 | 1429 | 1429
3.1 | Entrance Features | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 714 | 714
3.2 | Central Mail Station Re-Roofing | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 139 | 139 | 139 | 139
3.3 | Central Mailboxes Inventory | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704
3.4 | Summit Point Mail Station Re-Roofing | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 255 | 255 | 255 | 255 | 255 | 255 | 255 | 255 | 255
3.5 | Summit Point Mailboxes Inventory | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704
3.6 | Tot Lot & Outdoor Furniture | 9384 | 2599 | 2599 | 2599 | 2599 | 2599 | 2599 | 2599 | 2599 | 2599 | 2599 | 2599 | 2599 | 2599 | 2599 | 4049 | 4049 | 4049 | 4049 | 4049
3.7 | Basketball Court Restoration | 296 | 296 | 296 | 296 | 296 | 296 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324
3.8 | Basketball Standards | 352 | 352 | 352 | 352 | 352 | 352 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280
3.9 | Split-Rail Fencing | 553 | 553 | 933 | 933 | 933 | 1020 | 1020 | 1020 | 1114 | 1114 | 1114 | 1218 | 1218 | 1218 | 1330 | 1330 | 1330 | 1454 | 1454 | 1454
3.10 | Vinyl Fencing | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69
3.11 | Storm Water Drainage System Allowance | 3264 | 1263 | 1263 | 1263 | 1263 | 1263 | 1263 | 1263 | 1554 | 1554 | 1554 | 1554 | 1554 | 1554 | 1554 | 1911 | 1911 | 1911 | 1911 | 1911
ANNUAL COMPONENT CONTRIBUTION TOTALS |  | 61391 | 47783 | 44670 | 44670 | 46804 | 46891 | 128364 | 128364 | 135954 | 135954 | 143599 | 146138 | 154248 | 154248 | 79694 | 81501 | 51113 | 51237 | 53885 | 53885
COMPONENT METHOD SUMMARY |  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
BEGINNING RESERVE FUND BALANCE |  | 86906 | 124063.2921 | 160826.2555 | 127888.3245 | 175626.5626 | 154921.6265 | 202562.7229 | 238580.4646 | 373159.2013 | 263832.0526 | 406593.2058 | 303609.2301 | 436360.2637 | 329130.189 | 491702.7442 | 289893.0971 | 320955.7482 | 214871.1553 | 266886.6649 | 243514.9368
PLUS ANNUAL COMPONENT CONTRIBUTION |  | 61391 | 47783 | 44670 | 44670 | 46804 | 46891 | 128364 | 128364 | 135954 | 135954 | 143599 | 146138 | 154248 | 154248 | 79694 | 81501 | 51113 | 51237 | 53885 | 53885
CAPITAL EXPENDITURES |  | 26657 | 14045 | 81341 | 0 | 71564 | 2888 | 97834 | 0 | 254295 | 0 | 256355 | 21108 | 271967 | 0 | 292297 | 57178 | 164233 | 4117 | 83231 | 0
SUBTOTAL |  | 121640 | 157801.2921 | 124155.2555 | 172558.3245 | 150866.5626 | 198924.6265 | 233092.7229 | 366944.4646 | 254818.2013 | 399786.0526 | 293837.2058 | 428639.2301 | 318641.2637 | 483378.189 | 279099.7442 | 314216.0971 | 207835.7482 | 261991.1553 | 237540.6649 | 297399.9368
Balance Interest |  | 1754.1416 | 2504.1376 | 3246.1743 | 2581.3434 | 3544.909 | 3126.9932 | 4088.598 | 4815.593 | 7531.978 | 5325.28 | 8206.8219 | 6128.1567 | 8807.6508 | 6643.2808 | 9924.7031 | 5851.3054 | 6478.285 | 4337.0358 | 5386.9354 | 4915.1921
Contribution Interest |  | 669.1505 | 520.8258 | 486.8947 | 486.8947 | 510.1549 | 511.1032 | 1399.1437 | 1399.1437 | 1481.8733 | 1481.8733 | 1565.2023 | 1592.877 | 1681.2745 | 1681.2745 | 868.6498 | 888.3457 | 557.1222 | 558.4738 | 587.3365 | 587.3365
Originally Expenditure Interest - but this calculation removed with October 2008 version because core assumption of study calculations is that contributions and balance collect and accrue throughout the year, but that expenditures only occur at the end of the year - this no interest deduction is necessary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLUS INTEREST INCOME @ 2.00% |  | 2423.2921 | 3024.9634 | 3733.069 | 3068.2381 | 4055.0639 | 3638.0964 | 5487.7417 | 6214.7366 | 9013.8513 | 6807.1533 | 9772.0242 | 7721.0337 | 10488.9252 | 8324.5553 | 10793.3528 | 6739.6511 | 7035.4072 | 4895.5096 | 5974.2718 | 5502.5286
FULLY FUNDED RESERVE FUND BALANCE |  | 124063.2921 | 160826.2555 | 127888.3245 | 175626.5626 | 154921.6265 | 202562.7229 | 238580.4646 | 373159.2013 | 263832.0526 | 406593.2058 | 303609.2301 | 436360.2637 | 329130.189 | 491702.7442 | 289893.0971 | 320955.7482 | 214871.1553 | 266886.6649 | 243514.9368 | 302902.4653
| CURRENT FULLY FUNDED STATUS | 2012: 153.4%; 2014: TOTAL EXPENDITURES; 2016: 1699110; 2018: TOTAL CONTRIBUTIONS; 2021: 1790393; 2023: STUDY PERIOD TOTAL INTEREST; 2025: 124713.4653; 2027: AVERAGE ANNUAL CONTRIBUTION; 2029: 89519.65
FULLY FUNDED BALANCE GOAL

## DividerPhotos
PHOTOGRAPHS
WITH
DESCRIPTIVE NARRATIVES
Mason & Mason
Capital Reserve Analysts, Inc.